## Members
No. | Full name | Role | Note
1 | Võ Thành Lộc | PHP DEV | Team Lead
2 | Nguyễn Hoàng Long | PHP DEV
3 | Lê Quốc Cường | PHP DEV
4 | Đinh Việt Hoàng | PHP DEV
5 | Tô Đức Phương | PHP DEV
6 | Hồ Tấn Thuận | PHP DEV
7 | Mai Thị Thu Trang | QC
8 | Thân Trọng Huỳnh Nhân | QC
9 | Y Huynh Le Thien | ATE
10 | Tran Van Huy | ATE
11 | Nguyen Anh Dung | PM
12 | Tien Nguyen | TA / Mentor
https://join.skype.com/u4eIvl3Y4qg0

## Office Schedule
No. | Full name | Role | 2022-07-18 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-24 | 2022-07-25 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-07-31 | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-14 | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-21
1 | Võ Thành Lộc | PHP DEV | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO
2 | Nguyễn Hoàng Long | PHP DEV | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO
3 | Lê Quốc Cường | PHP DEV | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO
4 | Đinh Việt Hoàng | PHP DEV | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO
5 | Tô Đức Phương | PHP DEV | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO
6 | Hồ Tấn Thuận | PHP DEV | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO
7 | Mai Thị Thu Trang | QC | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO
8 | Thân Trọng Huỳnh Nhân | QC | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO
9 | Y Huynh Le Thien | ATE | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO
10 | Tran Van Huy | ATE | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO |  |  | WFH | WFH | WFH | WFH | WFH |  |  | WIO | WIO | WIO | WIO | WIO
11 | Nguyen Anh Dung | PM | WIO | WIO | WIO | WIO | WIO |  |  | WIO | WIO | WIO | WIO | WIO |  |  | WIO | WIO | WIO | WIO | WIO |  |  | WIO | WIO | WIO | WIO | WIO |  |  | WIO | WIO | WIO | WIO | WIO
12 | Tien Nguyen | TA / Mentor | WIO | WIO | WIO | WIO | WIO |  |  | WIO | WIO | WIO | WIO | WIO |  |  | WIO | WIO | WIO | WIO | WIO |  |  | WIO | WIO | WIO | WIO | WIO |  |  | WIO | WIO | WIO | WIO | WIO
WIO | Work In Office
WFH | Work From Home

## Training Time
No. | Full name | Role | 2022-07-18 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-24 | 2022-07-25 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-07-31 | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-14 | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-21
1 | Võ Thành Lộc | PHP DEV / TL | 1. PHP Training 10:00 - 12:00 2. HR Catch up 13:15 - 13:30 3. PHP Training 14:00 - 16:00
2 | Nguyễn Hoàng Long | PHP DEV | 1. PHP Training 10:00 - 12:00 2. HR Catch up 13:15 - 13:30 3. PHP Training 14:00 - 16:00
3 | Lê Quốc Cường | PHP DEV | 1. PHP Training 10:00 - 12:00 2. HR Catch up 13:15 - 13:30 3. PHP Training 14:00 - 16:00
4 | Đinh Việt Hoàng | PHP DEV | 1. PHP Training 10:00 - 12:00 2. HR Catch up 13:15 - 13:30 3. PHP Training 14:00 - 16:00
5 | Tô Đức Phương | PHP DEV | 1. PHP Training 10:00 - 12:00 2. HR Catch up 13:15 - 13:30 3. PHP Training 14:00 - 16:00
6 | Hồ Tấn Thuận | PHP DEV | 1. PHP Training 10:00 - 12:00 2. HR Catch up 13:15 - 13:30 3. PHP Training 14:00 - 16:00
7 | Mai Thị Thu Trang | QC | 1. HR Catch up 13:15 - 13:30
8 | Thân Trọng Huỳnh Nhân | QC | 1. HR Catch up 13:15 - 13:30
9 | Y Huynh Le Thien | ATE | 1. Automation Training 9:00 - 11:00 2. HR Catch up 13:15 - 13:30
10 | Tran Van Huy | ATE | 1. Automation Training 9:00 - 11:00 2. HR Catch up 13:15 - 13:30
11 | Nguyen Anh Dung | PM
12 | Tien Nguyen | TA / Mentor

## Sprint Planning
Sprint No. | Start Date | End Date | Duration | Sprint Goal
Sprint 0 | 2022-07-18 | 2022-07-19 | 2 days | Kick-off, Setup environments
Sprint 1 | 2022-07-20 | 2022-08-02 | 2 weeks | TBU - Deliverable 1
Sprint 2 | 2022-08-03 | 2022-08-16 | 2 weeks | TBU - Deliverable 2
Sprint 3 | 2022-08-17 | 2022-08-19 | 3 days | UAT and Closure

## Scrum Events
Sprint Cycle and Time Collaboration Timetable
Sprint | Week | Wed | Thu | Fri | Mon | Tue
Sprint 0 | Week 1 |  |  |  | Project Kick off (14:00 - 15:00) | Daily Meeting (9:30 - 9:45)
Sprint 1 | Week 1 | Sprint Planning (16:00 - 18:00) | Daily Meeting (9:30 - 9:45) | Daily Meeting (9:30 - 9:45) | Daily Meeting (9:30 - 9:45) | Daily Meeting (9:30 - 9:45)
| Week 2 | Daily Meeting (9:30 - 9:45) | Daily Meeting (9:30 - 9:45) | Daily Meeting (9:30 - 9:45) | Daily Meeting (9:30 - 9:45) | Daily Meeting (9:30 - 9:45)
[5 empty] | Sprint Refinement (15:00 - 16:00) | Sprint Review / Demo (15:00 - 15:30)
Sprint Release (17:00 - 18:00)
Sprint 2 | Week 1 | Sprint Retrospective (9:30 - 10:00) | Daily Meeting (9:30 - 9:45) | Daily Meeting (9:30 - 9:45) | Daily Meeting (9:30 - 9:45) | Daily Meeting (9:30 - 9:45)
Sprint Planning (10:00 - 12:00)
| Week 2 | Daily Meeting (9:30 - 9:45) | Daily Meeting (9:30 - 9:45) | Daily Meeting (9:30 - 9:45) | Daily Meeting (9:30 - 9:45) | Daily Meeting (9:30 - 9:45)
[5 empty] | Sprint Refinement (15:00 - 16:00) | Sprint Review / Demo (15:00 - 15:30)
Sprint Release (17:00 - 18:00)
Sprint 3 | Week 1 | UAT and Closing | UAT and Closing | UAT and Closing

## Size Estimation
| NT Standard USP definition - Modified Fibonacci | The standard user story point of NT that can apply for kind of Software Development, Maintenance Project, Application Development service if your project is a small to mid-size mobile/web project.
Size | Detail | Example
0 point | Item is already completed or is so small that it doesn't make sense to even give it a size number. However, too many 0 point story in a sprint is not good because 0 point doesn't mean no effort is required --> The team velocity will be impacted. | Verify whether a fix had been applied or not
0.5 point | Easy, no risk/complexity fix or minor feature | Implement confirmation dialog; modify/remove a UI element (a button or a field)
1 point | A straightforward task could be carried on by most inexperienced members of the team. Minor effort to implement and verify. | Add a field(s) to UI/API request/DB; forgot password form/request. Trivial/ Change static content, the same view for all users/ Change terminology, Sign out, Social media network links
2 points | Still a relatively straightforward, while more complex and higher in volume than "1" | Easy Simple function with simple design/ Sign in (simple), Sign up (simple), Breadcrumb, Navigation, Welcome screen.
3 points | Moderate in complexity or size; an average piece of work, that take some effort but does not introduces risks or technical debt | View content with simple design/ As an OL user I want to be able to view badged courses, User sign up functionality(complex); view user profile
5 points | Moderate to high complexity/size, some risks, a more complex and higher volume task that requires some analysis and thorough implementation | View content with a few content types, having many colors, elements, effects, behavior, Search, create, delete/ View content in grid and list without filter or sorting, Creating customer UI control (i.e. graph, timeline, etc.); advance search; object edit history)
8 points | High complexity/size, moderate risks/uncertainty. This should be the maximum size of a story that is acceptable to include in the sprint because of the level of risk for a sprint to success. | View complex content with many content types, filter, paging, ajax/ Display content item - Get inspired section homepage, refactor data storage layer for a big project; implement map with various data and filters on it
13 points | High risk/complexity/volume, high risks/uncertainty. Very risky to be included in the sprint, should try to break into smaller and more detailed stories. | View complex content with multi-level data, rules and constraints, Responsive design Latest page, TV and Radio page. Implement paginated news feed that support audio or video previews and various social activity and interaction; add table support for a phone app
20 points | Very high risk/complexity/volume, too many uncertainties to estimate properly. Risks/uncertainty. Very risky to be included in the sprint, should try to break into smaller and more detailed stories | Implement paginated news feed that support audio or video previews and various social activity and interaction; add table support for a phone app.
40 points | Very high risk/complexity/volume, too many uncertainties to estimate properly. Risks/uncertainty. Very risky to be included in the sprint, should try to break into smaller and more detailed stories | Implement paginated news feed that support audio or video previews and various social activity and interaction; add table support for a phone app.
100 points | Indicate that a story is so large, vague and ambiguous that it's pointless to estimate until further details are given. | In case a user story is too complex; it needs to be broken down into smaller storie
| What do 'Story Points' stay for? | Note
| A Story Point is a theoretical measure that expresses the difficulty level of any piece of work. The difficulty level is usually influenced by several factors such as the volume of work to do, the complexity of the work; any risk or uncertainty in doing the work. For example, removing some UI element, like a button, is an easy task, while developing tablet support for a smartphone app requires much more efforts. | - We can see the accuracy of the estimation greatly reduce if the story gets bigger. It's highly recommended to breakdown big story in to smaller stories
- Team effort means the total effort of all members in project team (including: PM, TA, BA, Dev, Tester)